## Internship-AI-26
Week 1: 5 days
Task | Overall Time (day) | Day | Group | PC | LLM (Local/API) | Data | Data Classification (private/Open-Source) | Team Guide | Risk of Completion | Work Setup
1. AI Tools overview | 0.5 | 1 | 1&2 | Personal |  |  |  | Badran |  | TBD
2. Building RAG System | 4.5 | 1 to 3 | 1&2 | Personal |  | DevSecOps / CIS Controls Guidelines | Open-Source
2.1 Parsing |  | 1 |  |  | Local
2.2 Chunking |  | 2 |  |  | Local
2.3 Embedding |  | 2 |  |  | Local
2.4 Vector DB Setup |  | 2 |  |  | weaviate
2.5 Ingestion |  | 3 |  |  | Local
2.6 Reranking |  | 3 |  |  | Local
2.7 Retrieval |  | 3 |  |  | Local
3. Building RAG Evaluation Pipeline | 4.5 | 4 to 5 | 1&2 | Personal
3.1: Eval Framework |  | 4
3.2: HITL Feedback |  | 5